## Sheet1
Test Planner and Tracker |  |  | Team 33 - InHobi
Test No. ID | Related Use case | Pre-conditions | Test Description (steps) | Expected Outcome | Sprint 2 Outcome (color code cell background) | Comments (if test case failed) | Sprint 3 Outcome (color code cell background) | Comments (if test case failed) | Sprint 4 Outcome (color code cell background) | Comments (if test case failed) | R1 Outcome (color code cell background) | Comments (if test case failed) | Sprint 5 Outcome (color code cell background) | Comments (if test case failed) | Sprint 6 Outcome (color code cell background) | Comments (if test case failed) | Sprint 7 Outcome (color code cell background) | Comments (if test case failed) | R2 Outcome (color code cell background) | Comments (if test case failed)
1 | User-Signup (One time only) |  | Fill the sign up form and hit submit | Able to log in with credentials on the log in page
2 | User login |  | Fill the correct login details and press login button | Able to succesfully login
|  |  | Fill in random/invalid login details and press login button | Throws error due to invalid email / password
|  |  | Fill in email field, leave password field empty, and hit login button | Throws error due to empty password field
3 | User Submitting Assignment |  | Upload correct assignment format | Able to submit assignment and sends it to community manager for grading |  | Not Implemented |  | Not Implemented
|  |  | Upload incorrect assignment format | Throws submission error |  | Not Implemented |  | Not Implemented
4 | Community Manager Grading Assignment |  | Approves of assignment | Unlocks next assignment for that particular student |  | Not Implemented |  | Not Implemented |  | Not Implemented
|  |  | Disapproves of assignment | Prompts student to resubmit assignment |  | Not Implemented |  | Not Implemented |  | Not Implemented
5 | Using Dashboard |  | Click on any registed courses | Redirects to lesson viewer page |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented
|  |  | Click on account settings | Redirects to settings page |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented
6 | Giving Rating, Reviews |  | Enter suitable reivew & give relevant rating | Rating + Review added to course's feedback |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented
7 | Course material addition |  | Fill in relevant course details (including name, syllabus, instructors, videos, assignments, etc.) | Able to succesfully create course and append to courses cataloge |  | Not Implemented |  | Not Implemented |  | Not Implemented
|  |  | Fill in course details with missing details (example: no assignments provided) | Throws error due to incomplete course content data |  | Not Implemented |  | Not Implemented |  | Not Implemented
|  |  | Disapproves of assignment | Prompts student to resubmit assignment |  | Not Implemented |  | Not Implemented |  | Not Implemented
8 | Viewing Course Page |  | Click on particular course to view (Purchased Course) | Display course dashboard (including user progress in assignments) |  | Not Implemented
|  |  | Click on particular course to view (Unpurchased Course) | Display unregistered course view (course syllabus, introductory video, etc.) |  | Not Implemented
9 | Using Course Group |  | Click on particular group (open or closed) | Display shared group messages |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented
|  |  | Send message on group | Add to course's messages thread & displays |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented
10 | Home Page |  | Go to homepage, scroll down to instructors tab | View Top 2 instructors and their courses |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented
|  |  | Go to homepage, scroll down to groups tab | View open groups with button to join |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented
11 | Bottom Navbar |  | check every page to see if its consistently displayed in same position and floats above other elements | Consistently displayed acrooss all page in all devices |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented |  | Not Implemented